## Sheet1
Module | Sub Module | flow | Status | Time Line | Delivery Date
Admin | Authencation | Login with email and password , forgot password with registered email (User will get email with link for resetting the password) | Done
| DashBoard | Stats of all Bids Related Information (Total Bids, Accepted and Rejected Bids), Category & Sub-Category wise Listing | Pending | 2021-09-20 | 21-09-2021 | Vardhan
| Customer | Listing of Customer Details with perferred ID (with prefix C) , Edit Name and status(Active & Inactive ) | Need to Deploy | 2021-09-20 | 21-09-2021 | Vardhan
| Customer | Filters and Search | Done
| Business Partner Managment | Listing of All Business Partners registered with vendor portal with perferred ID (with prefix V) | Done
| Business Partner Managment | Actions to Accept/ Hold & Reject , Email send to vendor & Notifcation send to vendor portal on Action | Done
| Business Partner Managment | View details for submitted from vendor | Done
| Business Partner Managment | Edit Vendor Details | Done
| Business Partner Managment | Manage Business Partner (Activate or Inactivate Vendor) , Email send to vendor & Notifcation send to vendor portal Status change | Done
| Business Partner Managment | Filters and Search | Done
| Business Partner Managment | Vendor Details with total Bid Amounts and subscription details | Pending | 21-09-2021 | 21-09-2021 | Ravi
| Category Managment | Listing of Categories | Done
| Category Managment | Add, Edit and Delete an Category | Done
| Category Managment | Listing of all Sub Categories | Done
| Category Managment | Add, Edit and Delete an Sub Category | Done
| Category Managment | Listing of All Ticketing Categories | Done
| Category Managment | Add, Edit and Delete an Ticketing Category | Done
| Category Managment | Filters and Search in Category | Need to check | 2021-09-20 | 21-09-2021 | Vardhan
| Category Managment | Filters and Search in Sub-Category | Need to check | 2021-09-20 | 21-09-2021 | Vardhan
| Category Managment | Filters and Search in Ticketing Category | Need to check | 2021-09-20 | 21-09-2021 | Vardhan
| Subscription Managment | Listing of all Subscriptions | Pending | 2021-09-20 | 21-09-2021 | Ravi
| Subscription Managment | Add / Edit Subscription | Pending | 2021-09-20 | 21-09-2021 | Ravi
| Subscription Managment | Filters and Search | Need to check | 2021-09-20 | 21-09-2021 | Vardhan
|  | Manage Subscribers Listing of Vendor who subscribes | Pending | 20-09-2021 | 21-09-2021 | Ravi
| Ticketing Managment | Listing of All Tickets created by Vendors | Done
| Ticketing Managment | Issue Display & Action to Close the Ticket with closure remarks | Done
|  | Email is send for vendor and admin with ticket details , Conversion is offline & Notification will send to Vendor Portal on Status | Need to check | 20-09-2021 | 21-09-2021 | Vardhan
| Ticketing Managment | Filters and Search | Done
| Change Password | Changing password | Done
| Notifications | Notications will trigger on Vendor Created and Ticket Raised | Done
Vendor | Registration | Sign up with email and mobile , User clicks on send Otp , OTP will be send to Email and Mobile no nagivates to verify OTP Page | Done
|  | Verify Otp Page with Email and Mobile Otp Fields On success validation user will nagivate to Regsiter details, Otp will be expires in 5 Mins, Resend OTP | Done
|  | On registration Details page will have Basic , Personal , Professional and Address , Validation with next and previous buttons with indivdual tab field validation | Done
|  | On Success creation , Email will be Send to Registered Email with crediatails to login and user nagivates to Subscription page (By default Vendor registered will be alloted free plan ) - Vendor can see all projects But, He cant bid. | Done
|  | User Clicks on Subscribe button on Monthly / yearly will be redirected to payment gateway page. | Pending | 21-09-2021 | 21-09-2021 | Ravi
|  | On successfull payment will send an email with plan details and nagivates to acknowlegement page. Vendor can redirect to login page from acknowlegdement Screen | Pending | 21-09-2021 | 21-09-2021 | Ravi
Vendor | Login | Login with email and password , forgot password with registered email (User will get email with link for resetting the password) | Done
| ACCOUNT - Pending | User will nagivate to profile page and vendor can see this pages (Testimonial,support and Change password) | Done
| ACCOUNT – Accepted | User will nagivate to place bids page and vendor can see this pages (Profile , place bids, My bids , change password and support ) | Done
| ACCOUNT – Hold | User will nagivate to profile page and vendor can see this pages (Testimonial,support and Change password) | Done
| ACCOUNT – Rejected | Vendor cant login , it will be redirects to login with error toast message | Done
| Profile page | Vendor can Edit his Basic and address details | Done
|  | Add / Edit /Delete Category and Images , Vendor cant add duplicate Categories and Sub categories Under Categories Session | Done
| Place Bids | Listing of Customer Requriements with summary info of requirements, Vendor can add to wish list , Post will be visible for 60 days from the date of creation | Pending
|  | Filters and Search based on categories,sub categories, location, time & bid range | Pending | 21-09-2021 | 21-09-2021 | Vardhan
| View Requriment details | View complete details of requirments , vendor can bid (only subscribed vendor) and view contact details (Only Go Pro Vendors and Bid Accepted vendor ) | Pending | 22-09-2021 | 22-09-2021 | Ravi
| My Bids | Listings of All pending , Accepted and Rejected Bidings. | Done
|  | For pending list will show a alert for Non-Go Pro Member(wait till bid acceptance), | Pending | 22-09-2021 | 22-09-2021 | Ravi
|  | For Accepted list will show a alert with Customer contact details | Done
|  | For Rejected list, will show an option to Re-bid. Vendor can view old Bid details with rejected | Pending | 22-09-2021 | 22-09-2021 | Ravi
| Testimonial Page | Listing of all Customer feedback for the vendor (Displaying Name , date of Feedback , Rating and Comments) | Need to Deploy
|  | Request an Testimonial with email address (Can enter multiple emails) , Email will be send with personalized message and template | Pending | 21-09-2021 | 21-09-2021 | Vardhan
| Support | Vendor can submit a ticket , Can List all Previous tickets with status and contact details of UBID | Need to Deploy
|  | If Vendor suppose to cliam the previous ticket is not resolved , Vendor can create a new ticket | Need to Deploy
| Notifications | Notications will trigger on Vendor profile status and Ticket status | Done
|  | On Bid Accepted / Rejected | Pending | 21-09-2021 | 21-09-2021 | Vardhan
| Change Password | Changing password | Done
Html Static Pages | Terms and conditions |  | Need to check | 20-09-2021 | 20-09-2021 | Durga
| Privacy Policy |  | Need to check | 20-09-2021 | 20-09-2021 | Durga
| Error Handling pages |  | Pending | 21-09-2021 | 21-09-2021 | Durga
All Modules | Issue fixing given by QA |  | Pending | 21-09-2021 | 23-09-2021 | Vardhan/Ravi
UAT Testing server with client

## Sheet2
Stats of all Bids Related Information (Total Bids, Accepted and Rejected Bids), Category & Sub-Category wise Listing | Pending | 2021-09-20
Listing of Customer Details with perferred ID (with prefix C) , Edit Name and status(Active & Inactive ) | Need to Deploy | 2021-09-20