## Sheet1
S.No | Module | Issue Description | Severity | Status
1 | Vendor/Registration | register page scrolling was coming for me please check that | tweak
2 | Vendor/Registration | 1.without enter the details click on check boxes and click on send otp 2.after showing the validation we enter the email and mobile number 3.it was showing the validations after entering the data the validation need to disappear. | tweak
3 | Vendor/Registration | 1.i gave the new email id and gave the existed oh no 2.it was showing the validation as " try with new email" show peoper validation. | major
4 | Vendor/Registration | 1.if click on mutiple time on send otp it was sending otps geeting multiple time otp to the mail. | major
5 | Vendor/Registration | 1.otp verification if we enter the incorrect number we are to delete the number it was not delteting | tweak
6 | Vendor/Registration | 1.reistration not geeting otp to the mobile number | major
7 | Vendor/Registration | 1.otp verification when we click on resend otp for multiple times it was geeting otp multiple times after clicking on ine time give loading | tweak
8 | Vendor/Registration | 1.otp verification the mobile number text has to start from the otp fields where they stared . | tweak
9 | Vendor/personal details | 1.without entering the data clcik on next it was showing validation in that we need to show the that text in red color | tweak
10 | Vendor/personal details | 1.the design for th profile pic have to change | tweak
11 | Vendor/basic details | 1.in the select aadhr proof in the field the drop down icon has to be in the middle | tweak
12 | Vendor/basic details | 1.select basic details files have to show hand icon for selection | tweak
13 | Vendor/professional details | 1.conform the text with the client (that services) | major
14 | Vendor/Address | 1.click on final submit after filling all the details it was showing something wentroungh message and redirecting to the login page | block
15 | vendor/registration | 1.the registration was not yet completed and closed and I started registring with the same details it was showing existed data it has to redirect to the page where we stoped . | major
16 | vendor/registration | 1.after succesful registration the logo in the join free for page was not same alligenment as the login and the registration. | major
17 | vendor/registration | 1.join free page the arrow icons was not looking good and they are overlaped on the text and line | tweak
18 | vendor/registration | 1.join free page the icons alligenment was not same. 2.the text where we showing the start that has to be highlated. | tweak
19 | vendor/registration | 1.join free trail page in the subscription plan iocn it was showing hand icon and clickable but it was not redirecting to anywhere check that once. | tweak
20 | vendor/registration | 1.profile view the company name and value text have to come side by side | tweak
21 | Vendor/Login | 1.login page password firld design was different | tweak
21 | Vendor/Login | 1.login page I am getting scrolling | tweak
22 | Vendor/Login | 1.need help popup need to give the proper ph no and mail id | tweak
23 | Vendor/Login/registartion | 1.we are getting some tost messages for those backgorund also showing no need to show background | tweak
24 | Vendor/Login | 1. login password field view icon was in opposite manner check that for not visable it has to show the view icon with cross check that . | tweak
25 | vendor/change password | 1.the design of the fields was distrubed 2.manidatory stars have to showin in red color 3.the validations also show in red color | major
26 | vendor/change password | 1.view icons are showing in the opposite direction if the password is visable the view icon was showing eye icon with the cross | major
27 | vendor/change password | 1.changing of password for vendors we have to ask them for special characters numarics also | tweak
28 | vendor/change password | 1. enter the new password conform password need to be different after getting the validations the vakues was disappering check that once. | tweak
29 | vendor/profile | 1.the left side text starting letter was not visable | tweak
30 | vendor/profile | 1.profile notifications icon was not coming check that once. | major | Done
31 | vendor/profile | 1.the logo at the left side was little bit small conform with the client once is it ok or not | tweak
32 | vendor/profile | 1.name and surname was coming in two lines check that | tweak | Done
33 | vendor/profile | 1.basic info edit the profile image name was not showing and the fields alliginment have to be same | tweak
34 | vendor/profile | 1.when I am trying to click on edit in the address it was not showing hand icon and and doing any function in that when the account status is pending | major
35 | vendor/profile | 1.in the registartion address we are showing land mark as optional but in the vendor profile land mark showing manidatory check that once. | tweak | Done
36 | vendor/profile | 1.address edit no need to show the cross icon in the field services | tweak
37 | vendor/profile | project details beside category name showing two colons check that once. | tweak | Done
38 | vendor/profile | project details we are updating the images they coming in a single line not side by side please check that once. | tweak | Done
39 | vendor/profile | project details click on edit it was not showing the subcategory name | tweak
40 | vendor/profile | project details for the icons at the right side add delete edit have to show hand icon | tweak
41 | vendor/profile | project details click on edit when we click on update it was not updating anything | block
42 | vendor/profile | project details when we click on the uplod icon in any category it was showing the popup label as profile status but in the below text it was showing select the service. | major | Done
43 | vendor/profile | project details for the upload icon also we have to show the hand icon | tweak
44 | vendor | session expire was not updated please check once. | major
45 | vendor/profile | we gave one image in profile that image was not showing clearly | major
46 | vendor/notifications | 1.the text we are showing that was not visable properly it was showing gray | tweak
47 | vendor/notifications | the recent notifucations have to come at the top | tweak
48 | admin/notifications | 1.new vendor registered the notification was not getting to admin portal | major
49 | Vendor/notifications | 1.when active and inactive the vendor not getting notifications and existed notification got changed | major
50 | Vendor/place bid | 1.filter,sort,search functionalitys was not working | block
51 | Vendor/place bid | 1.place bids listing it was showing posted 32min ago details page it was showing 2 dasys ago check that | major
52 | Vendor/place bid | 1.listing the post added to wishlist the button have to change to wishlisted like that or again when we are clicking it ha sto show already added | tweak
53 | Vendor/place bid | 1.for the post there is no attachment have to show text like no attachments not show any blank page | tweak
54 | Vendor/place bid | 1.post details if the post is added to wishlist have to wishlisted not add to wishlist | tweak
55 | Vendor/place bid | post details I am giving more than the amount gice by the customer it was taking and showing bid created | major | major
56 | Vendor/place bid | listing if we placed the bid it has to show some test like you are placed a bid like that | tweak
57 | Vendor/wishlist | click on place bid for the wishlisted product it was not doing any function | block | Done
58 | Vendor/my bids | 1.saerch,sort was not working check that once. | block
59 | Vendor/my bids | 1.when we click on contact it has to show any tostmessage or anything but now it was not showing anything check that once. | major
60 | Vendor/place bid | 1.when we placing a bid it wont take any negative values check that | major
61 | Vendor/my bids | 1. listing the price of yor bid was showing different check once | major
62 | Vendor/my bids | 1.for all the bids we need to change the labels. | tweak
63 | Vendor/my bids | 1.your bids time was not showing correct. | major
64 | Vendor/my bids | 1.need to change the date format in your bids | tweak
65 | Vendor/support | 1.give th correct ph no and mail id in the support page | tweak
66 | Vendor/support | 1.give clickable for the mail it has to redirect to our mailing platform | major
67 | Vendor/support | 1.click on submit ticket in that form don't enter anything and click on submit it was showing error in code manner | block
68 | Vendor/support | 1.click on submit ticket in that form have to show the manidatory fields | tweak
69 | Vendor/support | 1.click on submit ticket in that form click on close icon it was not doing any action check that | major
70 | Vendor/support | 1.submiting ticket form need to show the hand icon. | tweak
71 | Vendor/support | below tickets listing which status we are showing there
72 | Vendor/support | 1. when I click on submit for multiple times in admin it was genarating the same ticket multiple time please put the loadig | major
73 | Vendor/support | 1. in the tickects listing below it was showing clickable and hand icon in the ticket id but it was not redirecting to any where check that | tweak
74 | Vendor/support | 1.we have to show the ticket description also in the listing if the vendor rised multiple tickets with same title it will difficult to pick what they need. | major
75 | Vendor/support | in the created date no need to show the cammam beside the month | tweak
76 | Vendor/support | 1.ticket listing all the statuses are showing in green color only check once. | tweak
77 | Vendor/my bids | 1.rejected bid click on bid again it was we place the bid but the rejetced bid the same bid was showing there check that once. | major
78 | vendor/profile | 1.disable the testimonial tab | tweak
79 | vendor/profile | 1.i we are deleting any category which was there in the services 2.in the services also the category won't shown please check | major
80 | vendor/profile | 1.we are adding already existed category it was not showing any text like already exitesd | tweak
81 | vendor/profile | 1.images mouse hover we have to show the hand icon over there check once. | tweak
82 | vendor/profile | 1.for the images it was showing left and right side arrow icons there are very big and not looking good check once. | tweak
83 | vendor/my bids | 1.the text no bids there ha sto show at the middle check that once. | tweak
84 | vendor/profile | 1. the edit and the delete icons in the imges was not looking good | tweak
85 | vendor/profile | 1.images when I clickk on edit it was not showing the file name check once. | tweak
86 | vendor/profile | 1.when we clcik on the image the images was not showing fully check that once. | major
87 | vendor/profile | if the more text is there below the image have to put the readmore icon and the with proper displaying | major
88 | vendor/profile | 1.when we updating the profile the profile updating date is showing as the approved date check that | major
89 | vendor/profile | imgaes if the images rae no there or not there for more than 3 don’t show the arrows check that once. | tweak
90 | vendor/support | in the admin it was showing different ticket id and in the vendor notifications it was showing the different id check that once. | major
91 | vendor/my bids | 1.in the rejected bids click on bid again in that the details the view contact details was showing perpul color but it has to show in green check that once. | major
92 | vendor/my bids/place bids | it was showing some text like project 1 text for that give the name of the value please check once. | tweak
93 | vendor | 1. in all the pages we have to show the page nation if there are more bids it will difficult to scroll | major
94 | admin/customer | 1.customer id have to change please check | major
95 | admin/all tabs | 1.show proper text if the data is not there | tweak
96 | admin/customers | 1.search functionality was not working check that once. | major
97 | admin/business partner managemnt | 1.we need to change the all business partner managemnt to the pending business partenes(or) new business partner | tweak
98 | admin/business partner managemnt/customers | 1.click on view the design was distrbed and the manidatory stars have to show in red color | major
99 | admin/business partner managemnt/customers | 1.view details when we clcik on click here it has too show the text as editing mode like that | tweak
100 | admin/business partner managemnt/customers | view the profile photo design was not good check that once. | tweak
101 | admin/business partner managemnt | 1.when we inactive the vendor when they open their account it was showing everything immidate it has to show text like your account is inactive like that | major
102 | admin/business partner managemnt | 1.there is not options tho check the filters | block
103 | admin/business partner managemnt | 1.seach functionality was not working check that | major
104 | vendor/profile | 1.admin reject the vendor the test was more that text was over lapping on the dit icon check that once. | tweak
105 | admin/business partner managemnt | 1.click on view in that click update the landmark was not manidatory but it was showing error in code check that once. | block
106 | admin/business partner managemnt | 1.view if the vendor account is rejected or it was in hold no need to show the edit option to the admin | tweak
107 | admin/category managemnt | 1.category when we adding the new category it was not asking for any image please check that once. | major
108 | admin/category managemnt | 1.category edit when I am changing the status and click on update it was showing the validation of the category name | major
109 | admin/category managemnt | when we are deleting the existed category it was asking at the top for the conformation check that once | major
110 | admin/category managemnt | search functionality not working | major
111 | admin/category managemnt | I was inactive the category but it was visable to the vendor but it wont check that once. | major
112 | admin/category managemnt | adding sub category by default it was selected one category | tweak
113 | admin/category managemnt | when we inactive the parent category sub categorie also inactivaing but it was showing in the venodr | major
114 | admin/category managemnt | subcategorie click on edit it was not showing the file name | tweak
115 | vendor /wishlist | we added some posts into wishlist place the bids for wishkisted products the wishlist count was not decreasing check that once. | major
116 | vendor /profile | uploading the images the category text alligenment has to be same with the image bboxes check that once. | tweak
117 | admin/subscription | add subscription give proper validations for all the fields | major
118 | admin/subscription | add suscription we didn't given any field values and click on save it was showing error in code formate cehck that once. | block
119 | admin/subscription | filters there is no option to check the filters functionality check that once. | block
120 | admin/subscription | when I click on the filter the copyright text was coming upon the listing check that once. | tweak
121 | admin/subscription | click on view in that we can edit also make sure that view is only for viewing and fro editing we need saperate icon check once. | tweak
122 | admin/subscription | add new subscription give manidatory fields | major
123 | admin/subscription | we have to add the another filed as s.no check that once it will be dificult to count indivudual | tweak
124 | admin/Ticketing | when we cluck on that at the top it was showing datatable warning | major
125 | admin/Ticketing | there are no tickcets it has to show the text like no tickets found like that | tweak
126 | admin/important documents | have to give the serial numbers | tweak
127 | admin/important documents | click on add new document the design was not good test was not visable the copyrtight text was coming a little bit top cehck that once. | tweak
128 | admin/important documents | add new document the description text area was very small and the manidatory stars have to show in red color | tweak
129 | admin/important documents | add new document for save and back buttons it has to show the hand icon check that once. | tweak
130 | admin/important documents | add new document when I am tring to fill the details it was not working it was not accepting anything to enter the curser was not coming to that text area | major
131 | admin/important documents | add new document the upword arrow was not good and when we click on that it was not visable and not coming | tweak
132 | admin/important documents | when I click on add new document the design was changing completelty check that once. | major
133 | admin/important documents | I am tring to add any new document it was not working check that once. | block
134 | admin/important documents | edit of the existed document was not working check that once. | block
135 | admin/Ticketing | click on issue it was opening and label it was showing messge but it was issue make a note that change the label | tweak
136 | admin/Ticketing | click on ticket id in that it was opening the chat in that the vendor profile image was not coming check that once. | major
137 | vendor/register | the mobile number validation need to change it was not proper | tweak
138 | vendor/register | in the mobile number when we giving the 0's it was taking it has to show validation | tweak
139 | vendor/register | personal details profile pic I added the xlx file it was taking check that once. | major
140 | vendor/register | I am tring to remove or add the new profile image it was not changing check that once. | major
141 | vendor/register | when we update half details and click on refresh the previus what we updated those are missing check that once | major
142 | vendor/register | basic details when we uploading the xls file it was showing the validation at the top pleas eshow the proper validation. | major
143 | vendor/register | the text in the profisinal details the brackets was small and the text was big check that once. | tweak